## Bug Reports
Bug ID | User Type | Module | Bug Title | Severity | Status
BUG_STD_001 | standard_user | Checkout | Checkout accepts invalid pincode characters | Medium | Open
BUG_STD_002 | standard_user | Menu | Reset App State not functioning | High | Open
BUG_STD_003 | standard_user | Products | Product price changes unexpectedly | Critical | Open
BUG_PERF_001 | performance_glitch_user | Application Performance | UI responds slowly during navigation | Medium | Open
BUG_PROB_001 | problem_user | Product Listing | Product images replaced with dog images | High | Open
BUG_PROB_002 | problem_user | Navigation | About page not redirecting | Medium | Open
BUG_PROB_003 | problem_user | Checkout | Last name field not accepting input | Critical | Open
BUG_PROB_004 | problem_user | Product Filter | Product filter not functioning | High | Open
BUG_PROB_005 | problem_user | Application | Application gets stuck during usage | High | Open
BUG_ERR_001 | error_user | Product Sorting | Sorting functionality displays error | High | Open
BUG_ERR_002 | error_user | Checkout Validation | Checkout succeeds without last name | Critical | Open
BUG_ERR_003 | error_user | Cart | Add to Cart button not working for some items | Critical | Open
BUG_ERR_004 | error_user | Checkout | Finish button not functioning | Critical | Open
BUG_VIS_001 | visual_user | Product Listing | Incorrect dog image displayed | Medium | Open
BUG_VIS_002 | visual_user | Checkout UI | Checkout button visually misplaced | Low | Open
BUG_VIS_003 | visual_user | Header UI | Cart icon alignment issue | Low | Open
BUG_VIS_004 | visual_user | Product Sorting | Sorting visually inconsistent | Medium | Open

## Scenarios
Scenario ID | User Type | Module | Scenario Description | Priority
TS_001 | standard_user | Checkout | Verify checkout validates pincode input correctly | High
TS_002 | standard_user | Menu | Verify Reset App State functionality | High
TS_003 | standard_user | Products | Verify product prices remain consistent when selecting items | Critical
TS_004 | standard_user | Cart | Verify products can only be purchased after adding to cart | Medium
TS_005 | standard_user | Products | Verify product listing functionality | Medium
TS_006 | performance_glitch_user | Application Performance | Verify application response time during navigation | Medium
TS_007 | problem_user | Product Listing | Verify correct product images are displayed | High
TS_008 | problem_user | Application | Verify application does not freeze during usage | High
TS_009 | problem_user | Navigation | Verify About page redirects correctly | Medium
TS_010 | problem_user | Checkout | Verify Last Name field accepts user input | Critical
TS_011 | problem_user | Product Filter | Verify product filter/sorting functionality | High
TS_012 | locked_out_user | Login | Verify support/help options for locked out users | Low
TS_013 | error_user | Product Sorting | Verify sorting functionality works without errors | High
TS_014 | error_user | Checkout Validation | Verify checkout requires mandatory Last Name field | Critical
TS_015 | error_user | Cart | Verify Add to Cart functionality works for all products | Critical
TS_016 | error_user | Checkout | Verify Finish button completes checkout successfully | Critical
TS_017 | visual_user | Product Listing | Verify product images display correctly without visual glitches | Medium
TS_018 | visual_user | Checkout UI | Verify Checkout button alignment in UI | Low
TS_019 | visual_user | Header UI | Verify cart icon alignment in header | Low
TS_020 | visual_user | Product Sorting | Verify sorting UI displays correctly | Medium

## Test Cases
Test Case ID | Scenario ID | User Type | Module | Test Case Description | Steps | Expected Result | Actual Result | Status
TC_001 | TS_001 | standard_user | Checkout | Validate pincode input | Enter alphabets/special characters in pincode field | System should reject invalid characters | System accepts invalid characters | Fail
TC_002 | TS_002 | standard_user | Menu | Verify Reset App State | Add items to cart and click Reset App State | Cart should reset | Cart not cleared | Fail
TC_003 | TS_003 | standard_user | Products | Verify product price consistency | Click multiple products | Prices should remain fixed | Prices change unexpectedly | Fail
TC_004 | TS_006 | performance_glitch_user | Application Performance | Verify UI responsiveness | Navigate between product pages | Smooth navigation expected | UI responds slowly | Fail
TC_005 | TS_007 | problem_user | Product Listing | Verify correct product images | Open product page | Correct product images displayed | Dog images displayed | Fail
TC_006 | TS_008 | problem_user | Application | Verify application stability | Use application continuously | Application should not freeze | Application gets stuck | Fail
TC_007 | TS_009 | problem_user | Navigation | Verify About page navigation | Click About link | About page should open | No redirection occurs | Fail
TC_008 | TS_010 | problem_user | Checkout | Verify Last Name field | Try typing in Last Name field | Field should accept input | Unable to type | Fail
TC_009 | TS_011 | problem_user | Product Filter | Verify product filter | Apply sorting/filter | Products should sort correctly | Filter not functioning | Fail
TC_010 | TS_013 | error_user | Product Sorting | Verify sorting functionality | Use sorting dropdown | Products should sort properly | Error message displayed | Fail
TC_011 | TS_014 | error_user | Checkout Validation | Verify mandatory Last Name | Leave Last Name blank and continue | Validation error should appear | Checkout succeeds | Fail
TC_012 | TS_015 | error_user | Cart | Verify Add to Cart buttons | Add multiple products | All products added successfully | Some buttons not working | Fail
TC_013 | TS_016 | error_user | Checkout | Verify Finish button | Click Finish after checkout | Order should complete | Finish button unresponsive | Fail
TC_014 | TS_018 | visual_user | Checkout UI | Verify Checkout button alignment | Open checkout page | Button should align correctly | Button misplaced | Fail
TC_015 | TS_019 | visual_user | Header UI | Verify cart icon alignment | Open homepage | Cart icon should align properly | Cart icon misplaced | Fail

## Enhancements
Enhancement ID | Module | Suggestion | Benefit | Priority
ENH_001 | Checkout | Add Buy Now option | Faster purchasing process | Medium
ENH_002 | Products | Add product reviews and ratings | Improves customer trust | Low
ENH_003 | Checkout | Add payment options | Improves transaction functionality | High
ENH_004 | Order Management | Add order tracking | Better customer experience | Medium
ENH_005 | Products | Add wishlist/save for later feature | Improves user convenience | Medium
ENH_006 | Products | Add Load More option | Improves product browsing | Low
ENH_007 | Support | Add email support for users | Improves customer support | Medium
ENH_008 | Checkout | Add phone number input field | Improves contact verification | Medium
ENH_009 | Authentication | Add support option for locked-out users | Improves account recovery | High

## QA SUMMARY
QA SUMMARY REPORT
Project Name | Manual Testing of SauceDemo E-Commerce Application
Application Tested | SauceDemo Demo Website
Testing Type Performed | Functional Testing, UI Testing, Validation Testing, Navigation Testing, Performance Testing
Test Users Covered | standard_user, performance_glitch_user, problem_user, locked_out_user, error_user, visual_user
Modules Tested | Login, Products, Cart, Checkout, Navigation, Product Sorting, UI Components
Total Test Scenarios Created | 20
Total Test Cases Executed | 15
Total Bugs Identified | 14
Critical Bugs | 4
High Severity Bugs | 5
Medium Severity Bugs | 4
Low Severity Bugs | 1
Major Issues Identified | Checkout validation issues, incorrect product images, broken sorting/filtering, navigation issues, UI alignment problems, performance lag
Enhancement Suggestions Provided | Buy Now option, Reviews & Ratings, Wishlist, Order Tracking, Email Support, Payment Options
Testing Outcome | Application contains multiple functional, UI, and validation-related defects across different user profiles
Conclusion | Critical defects identified in checkout, product filtering, and cart functionality. Multiple UI and navigation issues impact user experience. Recommendations provided to improve usability and customer support.